## Product_Backlog
Product Name:	Robbie Robot System					Fields in blue expect your input!
Team ID:	Underground Robots

Name:	Andrew Break
Initials:	AB
Student ID:	1001144937

(Additional names for teams only)
Name:	Andrew Hernandez
Initials:	AH
Student ID:	1001176094

Name:	Warren Smith
Initials:	WS
Student ID:	1001171972

Name:
Initials:
Student ID:

Total Features	Left	Available	Completed	Sprint Ends
Total at Start	32	32
Sprint 1	32	32	0	Mar 28
Sprint 2	32	32	0	Apr 04
Sprint 3	32	32	0	Apr 11
Sprint 4	32	32	0	Apr 18
Sprint 5	32	32	0	Apr 25
Sprint 6	32	32	0	May 02

				Note: Priority of unfinished Features is subject to change at the end of each sprint at the whim of the Product Owner
				Sprint # (by team size)					Additional features may be proposed by the student / team but must be approved by the Product Owner in writing
Feature ID	Prio	Status	Actual Sprint #	1	2	3	4	Pts	Cml	As a...	I want to...	So that...	Type	Notes
CRP	1	CP		1	1	1	1	21	21	PM	create robot parts	I can define robot models	CLI	No menu required here – run program, create a part
NRM	2	CP		2	1	1	1	13	34	PM	define new robot models	RRS can sell them to our Beloved Customers	CLI	Menu needed – create parts, then create a robot model
CC	3	CP		2	1	1	1	5	39	BC	browse a catalog of robot models	I can buy one or more robots	CLI	Need to list robots models, then list parts in selected model
ANC	4	CP		3	2	1	1	3	42	PB	create a new Beloved Customer	I can keep track of who's buying our products	CLI	The usual name, customer number, phone number, and email address
ANSA	5	CP		3	2	1	1	3	45	PB	create a new Sales Associate	I can keep track of my employees' performance	CLI	Name and employee number at a minimum
RO	6	NS		3	2	2	1	8	53	SA	create a robot order for a Customer	I can sell robots and thus do my job well	CLI	Select robot model and quantity, show details with total price
SD	7	NS		3	2	2	2	13	66	PB	ensure persistence of the RRS data	we don't lose orders or historical data	CLI	(CLI) Write the data to the default filename and reload it next time the program runs
MW	8	NS		4	3	2	2	3	69	All	open a GUI main window	I can interact with RRS Manager with my mouse	GUI	No menu required here – run program, create a part
PD	9	NS		4	3	2	2	34	103	PM	create robot parts via GUI dialogs	I can define robot models	GUI	An fl_input centric approach is OK initially, but a custom dialog is worth bonus points (perhaps Create > Robot Part)
RMD	10	NS		5	4	3	3	21	124	PM	define new robot models via GUI dialogs	RRS can sell them to our Beloved Customers	GUI	Similar to robot parts (perhaps Create > Robot Model)
CD	11	NS		6	4	3	3	8	132	BC	browse a catalog of robots via a GUI report	I can buy one or more robots	GUI	A text output is OK initially, but an attractive HTML-like output is desired (perhaps Report > All Robot Models)
	12	NS			5	4	3	21	153	SA	create a robot order for a Customer via GUI	I can sell robots and thus do my job well	GUI	As with CLI (and you’ll need the CLI to add BC and SA people)
	13	NS			5	4	4	13	166	PB	manage a robot order for a Customer via GUI	I can ensure the robot is built and ships	GUI	This will involve a state machine implementation
	14	NS			5	4	4	8	174	PB	create a new Beloved Customer via GUI	I can keep track of who's buying our products	GUI	The usual name, address, phone number, and email address (perhaps Create > Customer)
AD	15	NS			5	4	4	5	179	PB	create a new Sales Associate via GUI	I can keep track of my employees' performance	GUI	Name and employee number at a minimum (perhaps Create > Sales Associate)
	16	NS			6	5	4	13	192	BC	see pictures of the robots in the GUI catalog	I can see what I'm buying	GUI	Add picture when defining robot model, and show it in the robot model report
	17	NS			6	5	4	5	197	PB	allow the users to save data explicitly via GUI	we can save data without exiting the program	GUI	Write the data to the default filename on command (perhaps File > Save to the default filename)
	18	NS			6	5	4	8	205	PB	allow the users to load data explicitly via GUI	we can manage multiple stores in different files	GUI	Read the data from a user-selected file on command (perhaps File > Open)
	19	NS			6	5	4	8	213	PB	allow the users to save data to a specified name via GUI	we can manage multiple stores in different files	GUI	Write the data to a user-selected file on command and make that fie the default (perhaps File > Save As)
	20	NS				5	5	13	226	PB / SA	view a report of orders per SA in the GUI	I can estimate the value of employees / / I can justify a raise	GUI	A basic text report is fine (perhaps Report > Orders by Sales Associate)
	21	NS				6	5	21	247	All	enable basic login by role and customize the GUI	we don't have options that don't apply to our roles	GUI	User ID might be “sa” for Sales associate with a default password, via a dialog on launch (i.e., in main()),and then make inapplicable menu items inactive – keep it simple
	22	NS				6	5	13	260	All	enable copy and paste from text fields	we can save typing	GUI	Just implement this where the toolkit supports it – not all text widgets do, but it's easy where it's supported
	23	NS				6	6	13	273	BC	view my bill (invoice) in the GUI	I can pay for my robots	GUI	A basic text report is fine initially, but a more attractive HTML report is desired (perhaps Report > Invoice)
	24	NS					6	8	281	BC	view my orders in the GUI	see what I have coming to me	GUI	A basic text report is fine initially, but a more attractive HTML report is desired (perhaps Report > Orders by Customer)
	25	NS					6	8	289	SA	view a sales report in the GUI	I can justify a raise	GUI	A basic text report is fine (perhaps Report > Orders by Sales Associate)
	26	NS					6	8	297	PB	view a report of all orders in the GUI	I can manage the company	GUI	A basic text report is fine (perhaps Report > All Orders)
	27	NS					6	13	310	All	Add multi-level undo	Worry less about making mistakes	GUI	This would be for each Create event (e.g., a new Customer) only (perhaps Edit > Undo)
	28	NS					21	331	BC	see a pie chart of a model's component costs	I can decide if I want a different model	GUI	Consider using Fl_Chart, q.v., (perhaps Report > Robot Model Cost Breakdown)
	29	NS					13	344	SA	create a bulk (2+) order for Customer via GUI	avoid proliferation of orders and paperwork	GUI	Allow more than one robot model (with respective quantity) on a single order
	30	NS					8	352	PM	hide robot parts via GUI	obsolete parts aren't accidentally used	GUI	Mark robot parts as “obsolete” and don't allow adding them to new robot models
	31	NS					8	360	PM	hide robot models via GUI	obsolete robots aren't ordered	GUI	Mark robot models as “obsolete” and don't allow adding them to new orders
	32	NS					21	381	SA	save a draft order and return to it later via GUI	I can multi-task between indecisive customers	GUI	Save an order that hasn't been complete, and allow SA to resume work on it later
Product Backlog Burn Chart
Features Remaining at Start of Sprint
Sprints

## Sprint_#1
Sprint #	1
Start on	3/21/17 12:00 AM
End on	3/28/17 12:00 AM
Demo on	TBA

Total Tasks	10
Day 1 Left	10
Day 2 Left	10
Day 3 Left	10
Day 4 Left	10
Day 5 Left	8
Day 6 Left	4
Day 7 Left	4

Task ID	Feature ID	Category	Type	Assigned To	Description	Status	Notes
	CRP			WS	Create Robot parts	CP
	CRP			WS	Test robot parts code	CP
	NRM			AB	Allow for new robot models to be created	NF
	NRM			AB	Test code for adding new robot models	NF
	CC			AH	Create catalog of robot models	NF
	CC			AH	Test the catalog	NF
	ANC			AH	Add a new customer	CP
	ANC			AH	Test adding new customers	CP
	ANSA			AB	Add a new sales associate	CP
	ANSA			AB	Tests adding a sales associate	CP
Sprint Burn Chart
Tasks
Days

## Sprint_#2
Sprint #	2
Start on	3/28/17 10:00 AM
End on	4/4/17 10:00 AM
Demo on	TBA

Total Tasks	12
Day 1 Left	12
Day 2 Left	12
Day 3 Left	12
Day 4 Left	12
Day 5 Left	10
Day 6 Left	6
Day 7 Left	0

Task ID	Feature ID	Category	Type	Assigned To	Description	Status	Notes
CO	RO	CODE	CLI	AH	Create a robot order object	CP
COT	RO	TEST	CLI	AH	Verify that order holds needed information properly	CP
SDS	SD	CODE	CLI	WS	Implement a save data function within shop class	CP
SDST	SD	TEST	CLI	WS	Verify that data can be saved to .rrs format	CP
SDO	SD	CODE	CLI	WS	Implement an open data function within shop class	CP
SDOT	SD	TEST	CLI	WS	Verify that data can be reloaded to the system from .rss format	CP
WIN	MW	CODE	GUI	AB	Implement a dialogue that contains each area of the system, including RRS data	CP
WINT	MW	TEST	GUI	AB	Verify that all functions of main menu work as intended	CP
CP	PD	CODE	GUI	AB	Implement a GUI interface for creating robot parts	CP
CPT	PD	TEST	GUI	AB	Verify that all types of robot parts can be created in the GUI	CP
MREF		CODE	CLI	AB	Simplify view implementation	CP
CSF		CODE	CLI	WS	Create shop directory that incorporates sales data	CP
CPF		CODE	CLI	WS	Create associates directory that incorporates users	CP
Sprint Burn Chart
Tasks
Days

## Sprint_#3
Sprint #	3
Start on	4/4/17 10:00 AM			Sprint Burn Chart / Days / Tasks
End on	4/11/17 10:00 AM
Demo on	TBA

Total Tasks	8
Day 1 Left	8
Day 2 Left	8
Day 3 Left	8
Day 4 Left	4
Day 5 Left	4
Day 6 Left	0
Day 7 Left	0

Task ID	Feature ID	Category	Type	Assigned To	Description	Status	Notes
CM	RMD	CODE	GUI	AB	Create GUI dialog that allows user to create robot model	CP
CMT	RMD	TEST	GUI	AB	verify that dialog interface creates a new robot model	CP
VC	CD	CODE	GUI	AH	Create GUI dialog that displays the catalog of robot models	CP
VCT	CD	TEST	GUI	AH	verify that all robot models can be viewed via GUI dialog	CP
CA	AD	CODE	GUI	AH	Create GUI dialog that allows user to create new sales associate	CP
CAT	AS	TEST	GUI	AH	verify that a new sales associate can be created via GUI dialog	CP
RD	SD	CODE	CLI	WS	Refactor data persistance implementation	CP
RDT	SD	TEST	CLI	WS	Create CLI regression test to create and load save data	CP